## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | team-project-2231-swen-261-07-e-thegroup
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As an adopter I want to see a list of pets so that I can choose what to adopt | GIVEN I want to see a list of pets WHEN I search for list of pets THEN the system should return the list of pets that fits my criteria | Pass | fj;10/27
As a Owner I want to login so I can login into the system as admin and do things | Given I want to login as admin when I put in the correct username and password then I expect to login as admin and be able to perform all admin tasks | Pass | fj;10/26
| Given I want to login as admin when I put in the incorrect username and password then the system should return an error code | Pass | fj;10/26
As a Owner I want to logout so I can logout of the system so no one can access as admin if I’m not using the app anymore | Given I want to logout when I click the logout button then I expect to be logged out and not be an admin anymore | Pass | aj;10/26
As an adopter, I want to add pets to my adoption list so that I can adopt them | GIVEN I'm a user who wants a pet WHEN I add a pet to my adoption basket THEN I expect to see the pet in my adoption basket | Pass | al;10/23
As an adopter, I want to remove pets so that I can remove the pets I can’t adopt anymore from my list | GIVEN I have pets in my adoption basket WHEN I remove the pets from the basket THEN I expect the pet to not be there anymore | Pass | fj;10/25
| GIVEN I don't have pets in my adoption basket WHEN I remove the pets from the basket THEN I expect a message saying I don't have a pet in the basket | Pass | fj;10/25
As an Owner I want to add and remove pets so that buyers know which Animals are available | GIVEN a new pet needs to be adopted WHEN I add the new pet THEN I expect the user to be able to see the pet | Pass | al;10/27
| GIVEN a pet is no longer up for adoption WHEN I remove the pet THEN I expect the user to no longer see the pet | Pass | hl;10/27
| GIVEN a pet's information has changed WHEN I try to change the pet's information THEN I expect the information to change | Pass | hl;10/27
As an adopter, I want to have my data backed up so that everything is the same when I leave the app and come back | GIVEN something was changed in the system by the user WHEN the user leaves and come back THEN everything should look exactly the same as when the user left |  |  | Pass | fj; 11/12
As an adopter I want to see a list of pets so that I can know what I have adopted | GIVEN I've adopted pets WHEN I check my purchase history THEN I expect to see those pets in there |  |  | Pass | al; 11/12
| GIVEN I've not adopted pets WHEN I check my purchase history THEN I expect to see nothing there |  |  | Pass | al; 11/12
As an adopter I want to adopt so that I adopt the pets | GIVEN I have pets in my adoption basket WHEN I click the adopt button THEN I expect them to be out of the basket and ready for me to go adopt them |  |  | Pass | aj; 11/12
| GIVEN I don't have pets in my adoption basket WHEN I want to adopt THEN I expect the adopt button to be not there |  |  | Pass | aj; 11/12
As an adopter I want to login so I can login into the app and adopt pets | Given I want to login as an user when I put in the correct username and password then I expect to login as user and be able to perform all user tasks |  |  | Pass | hl; 11/12
| Given I want to login as an user when I put in the incorrect username and password then the system should return an error code |  |  | Pass | hl; 11/12
As an adopter I want to donate so that the organization can continue | GIVEN I've put in all the required fields WHEN I click the donate button I expect to see that I've donated successfully |  |  | Pass | fj; 11/14
| GIVEN I've missed some of the required fields or some fields are incorrect WHEN I click the donate button I expect to see an error |  |  | Pass | fj; 11/14
As an adopter I want to see notifications so I’m up to date with pets in my basket | GIVEN someone has adopted a pet that's in my basket WHEN I log in as a user THEN I expect to see a notification about the pet in my basket being adopted by someone else |  |  | Pass | al; 11/14
As an admin I want to see notifications so I know when someone donated or a pet has been adopted | GIVEN someone has adopted a pet WHEN I log in as admin THEN I expect to see a notification of the person adopting the pet |  |  | Pass | al; 11/14
| GIVEN someone has donated money WHEN I log in as admin THEN I expect to see notification about the person donating money |  |  | Pass | al; 11/14